## Sheet1
Schedule- Jashwanth Reddy
Building maps using slam on image sequences
S No. | Task | Expected Days to Complete | Status | Deliverable
1 | review of papers , literature on internet | 15 | ongoing | presentation
2 | panorama of images | 7 | ongoing | matlab code
3 | images radial distortion removal etc.. | 7 | to do | matlab code
4 | calibrating camera | 7 | to do | matlab code
5 | building 3-D model | 10 | to do | matlab code
6 | improving and finding new algorithm | 15 | to do | code and presentation